## 2. Project Dashboard
Silent Runner
Internal Use
Product burndown and metrics
| Sprint | SP | SPR | %SP | %Var(h) | BV | BVR | %BV | End Sprint | Sprint | Test | Passed | Failed | Notes
| S01 | [8 empty] | S01
| S02 | [8 empty] | S02
| S03 | [8 empty] | S03
| S04 | [8 empty] | S04
| Remain | [8 empty] | Remain
| TOTALS | [8 empty] | TOTALS | 0 | 0 | 0
Sprint progress - Updated on | [5 empty] | 2010-04-08
Sprint Current (01)
Estimates (h)
| Planned | Worked | EETC | %Var
| 100 | 1 | 0 | -99%
Story Points
| Planned | Final |  | %Var
Progress
Sprint 01 - Objective
Sprint 01 - Feedback
<Please provide your opinion about this sprint deliverable by sending us an e-mail.>

## 3. Resources
Silent Runner
Uso Interno
Resources
Team Performance
2010-04-08
[12 empty] | Days left | Hours Left
[12 empty] | 2 | 0
Daily Productivity Goal (h)
4
Team daily productivity average (h)
7.76
Chances to Complete (%)
Impact on Progress | [11 empty] | 100%
Team efficiency over 75%
76%
Team efficiency over 100%
65%
Team Progress and Efficiency
Sprint burndown
10 | Planned | 2010-03-29 | 2010-03-30 | 2010-03-31 | 2010-04-01 | 2010-04-02 | 2010-04-03 | 2010-04-04 | 2010-04-05 | 2010-04-06 | 2010-04-07 | 2010-04-08 | 2010-04-09 | 2010-04-10 | 2010-04-11
|  | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31
Day | 10 | 10 | 9 | 8 | 7 | 6 | 5 | 5 | 5 | 4 | 3 | 2 | 1 | 0 | 0
Story Points (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual (h) | 100 | 69.85 | 69.85 | 69.85 | 69.85 | 69.85 | 69.85 | 69.85 | 69.85 | 69.85 | 69.85 | 69.85 | 69.85 | 69.85 | 69.85
Remaining (h) | 100 | 60 | 48.5 | 31.5 | 25.5 | 19.5 | 19.5 | 19.5 | 15.5 | 13 | 8 | 0 | 0 | 0 | 0
Productive hours (Time Sheet) | 0 | 9.85 | 11.5 | 17 | 6 | 6 | 0 | 0 | 4 | 2.5 | 5 | 8 | 0 | 0 | 0
Cumulative Hours (Actual hours) | 0 | 9.85 | 21.35 | 38.35 | 44.35 | 50.35 | 50.35 | 50.35 | 54.35 | 56.85 | 61.85 | 69.85 | 69.85 | 69.85 | 69.85
New Tasks (hours) | 0 | -30.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target daily hours | 0 | 10 | 6.6667 | 6.0625 | 4.5 | 4.25 | 3.9 | 3.9 | 3.9 | 3.875 | 4.3333 | 4 | 0 | 0 | 0
Daily missed hours | 0 | -0.15 | 4.8333 | 10.9375 | 1.5 | 1.75 | -3.9 | -3.9 | 0.1 | -1.375 | 0.66667 | 4 | 0 | 0 | 0
Daily productive hours (AVG) |  | 9.85 | 10.68 | 12.78 | 11.09 | 10.07 | 8.39 | 8.39 | 9.06 | 8.12 | 7.73 | 7.76 | 6.99 | 6.35 | 6.35
Chances to Complete (%) | 100% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Team efficiency over (75%) | 100% | 97% | 105% | 125% | 109% | 99% | 0% | 0% | 89% | 80% | 76% | 76% | 69% | 0% | 0%
Team efficiency over (100%) | 100% | 82% | 89% | 107% | 92% | 84% | 0% | 0% | 76% | 68% | 64% | 65% | 58% | 0% | 0%
Projection based on total hours avaiable using 75% productivity target
Target daily hours | 10.2 | 10.2 | 10.2 | 10.2 | 10.2 | 10.2 | 0 | 0 | 10.2 | 10.2 | 10.2 | 10.2 | 10.2 | 0 | 0
Secured limit | 102 | 91.8 | 81.6 | 71.4 | 61.2 | 51 | 51 | 51 | 40.8 | 30.6 | 20.4 | 10.2 | -1.4211e-14 | -1.4211e-14 | -1.4211e-14
Projection based on total ideal hours avaiable using 100% productivity target
Target daily hours | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 0 | 0
Risk limit | 120 | 108 | 96 | 84 | 72 | 60 | 60 | 60 | 48 | 36 | 24 | 12 | 0 | 0 | 0
Impediments
Day |  | 2010-03-29 | 2010-03-30 | 2010-03-31 | 2010-04-01 | 2010-04-02 | 2010-04-03 | 2010-04-04 | 2010-04-05 | 2010-04-06 | 2010-04-07 | 2010-04-08 | 2010-04-09 | 2010-04-10 | 2010-04-11
New
Closed
Impediments
Team planned hours | bar: 2010-03-29 to 2010-04-06
Resource name | Type | Ideal Hours | % Prod | Hrs disp | Days | Total Prod (h) | Total Ideal (h) | Actual(h) | % Var 85% | % Var 100%
Max | PRG | 4 | 85% | 3.4 | 10 | 34 | 40 | 21 | 61.76% | 52.5%
Caio | GD | 3 | 85% | 2.55 | 10 | 25.5 | 30 | 1.35 | 5.294% | 4.5%
Kojiio | ART | 4 | 85% | 3.4 | 10 | 34 | 40 | 35.5 | 104.4% | 88.75%
Caio Audio | AUD | 1 | 85% | 0.85 | 10 | 8.5 | 10 | 12 | 141.2% | 120%
|  | 0 | 85% | 0 | 10 | 0 | 0 | 0 | 0% | 0%
|  | 0 | 85% | 0 | 10 | 0 | 0 | 0 | 0% | 0%
|  | 0 | 85% | 0 | 10 | 0 | 0 | 69.85 | 0% | 0%
|  | 0 | 85% | 0 | 10 | 0 | 0 | 0 | 0% | 0%
|  | 0 | 85% | 0 | 10 | 0 | 0 | 0 | 0% | 0%
|  | 0 | 85% | 0 | 10 | 0 | 0 | 0 | 0% | 0%
TOTAL |  | 2010-03-29: 12; 2010-03-31: 10.2; 2010-04-02: 102; 2010-04-03: 120; 2010-04-04: 69.85; 2010-04-05: 68.48%; 2010-04-06: 58.21%
Resource Status | bar: 2010-03-29 to 2010-04-05
Resource name | Worked Days | 2010-03-29: EETC; 2010-03-30: Work; 2010-03-31: Percent done; 2010-04-01: Productivity (h/day); 2010-04-02: Productivity Percent; 2010-04-03: Ideal Productivity Percent; 2010-04-04: Produtivity Target (h/day); 2010-04-05: Impediments
Max | 9 | 2010-03-29: 0; 2010-03-30: 21; 2010-03-31: 100%; 2010-04-01: 2.3333; 2010-04-02: 68.63%; 2010-04-03: 58.33%; 2010-04-04: 0; 2010-04-05: 0
Caio | 9 | 2010-03-29: 0; 2010-03-30: 1.35; 2010-03-31: 100%; 2010-04-01: 0.15; 2010-04-02: 5.882%; 2010-04-03: 5%; 2010-04-04: 0; 2010-04-05: 0
Kojiio | 9 | 2010-03-29: 0; 2010-03-30: 35.5; 2010-03-31: 100%; 2010-04-01: 3.9444; 2010-04-02: 116%; 2010-04-03: 98.61%; 2010-04-04: 0; 2010-04-05: 0
Caio Audio | 9 | 2010-03-29: 0; 2010-03-30: 12; 2010-03-31: 100%; 2010-04-01: 1.3333; 2010-04-02: 156.9%; 2010-04-03: 133.3%; 2010-04-04: 0; 2010-04-05: 0
0 | 9 | 2010-03-29: 0; 2010-03-30: 0; 2010-03-31: 100%; 2010-04-01: 0; 2010-04-02: 0%; 2010-04-03: 0%; 2010-04-04: 0; 2010-04-05: 0
0 | 9 | 2010-03-29: 0; 2010-03-30: 0; 2010-03-31: 100%; 2010-04-01: 0; 2010-04-02: 0%; 2010-04-03: 0%; 2010-04-04: 0; 2010-04-05: 0
0 | 9 | 2010-03-29: 0; 2010-03-30: 69.85; 2010-03-31: 100%; 2010-04-01: 7.7611; 2010-04-02: 0%; 2010-04-03: 0%; 2010-04-04: 0; 2010-04-05: 0
0 | 9 | 2010-03-29: 0; 2010-03-30: 0; 2010-03-31: 100%; 2010-04-01: 0; 2010-04-02: 0%; 2010-04-03: 0%; 2010-04-04: 0; 2010-04-05: 0
0 | 9 | 2010-03-29: 0; 2010-03-30: 0; 2010-03-31: 100%; 2010-04-01: 0; 2010-04-02: 0%; 2010-04-03: 0%; 2010-04-04: 0; 2010-04-05: 0
0 | 9 | 2010-03-29: 0; 2010-03-30: 0; 2010-03-31: 100%; 2010-04-01: 0; 2010-04-02: 0%; 2010-04-03: 0%; 2010-04-04: 0; 2010-04-05: 0
TEAM | 9 | 2010-03-29: 0; 2010-03-30: 69.85; 2010-03-31: 100%; 2010-04-01: 7.7611; 2010-04-02: 76.09%; 2010-04-03: 64.68%; 2010-04-04: 0; 2010-04-05: 0
Daily Report (scrum task + my tasks) from Target Process
Resource name | Total | 2010-03-29 | 2010-03-30 | 2010-03-31 | 2010-04-01 | 2010-04-02 | 2010-04-03 | 2010-04-04 | 2010-04-05 | 2010-04-06 | 2010-04-07 | 2010-04-08 | 2010-04-09 | 2010-04-10 | 2010-04-11
Max | 21 | 0 | 1.5 | 6 | 2 | 2 | 0 | 0 | 0 | 2.5 | 3 | 4 | 0 | 0 | 0
Caio | 1.35 | 1.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kojiio | 35.5 | 4.5 | 6 | 7 | 4 | 4 | 0 | 0 | 4 | 0 | 2 | 4 | 0 | 0 | 0
Caio Audio | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 69.85 | 9.85 | 11.5 | 17 | 6 | 6 | 0 | 0 | 4 | 2.5 | 5 | 8 | 0 | 0 | 0
Impediments | bar: 2010-03-29 to 2010-04-05
Description |  | 2010-03-29: IBL; 2010-04-01: Found Date; 2010-04-02: Closed Date; 2010-04-03: Solution

## 4. Timesheet
Silent Runner
Uso Interno
Timesheet
Sprint Backlog Items
IBL Name | Baseline [h] | Actual [h] | Done [h] | Resource name |  | Type | Compl [%] | Report | [13 empty] | Remaining [h] | Story Points | Var [%] | Var [h]
[8 empty] | 2010-03-29 | 2010-03-30 | 2010-03-31 | 2010-04-01 | 2010-04-02 | 2010-04-03 | 2010-04-04 | 2010-04-05 | 2010-04-06 | 2010-04-07 | 2010-04-08 | 2010-04-09 | 2010-04-10 | 2010-04-11
[8 empty] | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31
Sprint Backlog | 100 | 69.85 | 69.85 |  |  |  | 100% | 9.85 | 11.5 | 17 | 6 | 6 | 0 | 0 | 4 | 2.5 | 5 | 8 | 0 | 0 | 0 | 0 |  | -30.15% | -30.15
FEATURE 01
Jump | 10 | 11.5 | 11.5 | Max |  | PRG | 100% | 2010-03-30: 1.5; 2010-03-31: 6; 2010-04-01: 2; 2010-04-02: 2 | 0 |  | 15% | -1.5
Jump | 3 | 8.3 | 8.3 | Kojiio |  | ART | 100% | 2010-03-29: 0.3; 2010-03-30: 1; 2010-03-31: 1; 2010-04-01: 1; 2010-04-02: 1; 2010-04-05: 2; 2010-04-07: 2 | 0 |  | 176.7% | -5.3
Jump | 4 | 0.15 | 0.15 | Caio |  | GD | 100% | 2010-03-29: 0.15 | 0 |  | -96.25% | 3.85
Collision | 2 | 1 | 1 | Max |  | PRG | 100% | [14 empty] | 0 |  | -50% | 1 | bar: 2010-04-06
Collision | 8 | 2.3 | 2.3 | Kojiio |  | ART | 100% | 2010-03-29: 0.3; 2010-03-30: 1; 2010-03-31: 1 | 0 |  | -71.25% | 5.7
Double Jump | 2 | 1 | 1 | Max |  | PRG | 100% | [14 empty] | 0 |  | -50% | 1 | bar: 2010-04-06
Double Jump | 3 | 0.3 | 0.3 | Kojiio |  | ART | 100% | 2010-03-29: 0.3 | 0 |  | -90% | 2.7
Double Jump | 4 | 0.15 | 0.15 | Caio |  | GD | 100% | 2010-03-29: 0.15 | 0 |  | -96.25% | 3.85
Camera Movement | 3 | 0.5 | 0.5 | Max |  | PRG | 100% | 2010-04-06: 0.5 | 0 |  | -83.33% | 2.5
Camera Movement | 4 | 0.15 | 0.15 | Caio |  | GD | 100% | 2010-03-29: 0.15 | 0 |  | -96.25% | 3.85
Walljump | 2 | 4 | 4 | Max |  | PRG | 100% | 2010-04-08: 4 | 0 |  | 100% | -2
Walljump | 3 | 6.3 | 6.3 | Kojiio |  | ART | 100% | 2010-03-29: 0.3; 2010-03-30: 1; 2010-03-31: 1; 2010-04-08: 4 | 0 |  | 110% | -3.3
Walljump | 4 | 0.15 | 0.15 | Caio |  | GD | 100% | 2010-03-29: 0.15 | 0 |  | -96.25% | 3.85
Wall Climb | 2 | 0 | 0 | Max |  | PRG | 0% | [14 empty] | 0 |  | -100% | 2
Wall Climb | 6 | 2.3 | 2.3 | Kojiio |  | ART | 100% | 2010-03-29: 0.3; 2010-03-30: 1; 2010-03-31: 1 | 0 |  | -61.67% | 3.7
Wall Climb | 4 | 0.15 | 0.15 | Caio |  | GD | 100% | 2010-03-29: 0.15 | 0 |  | -96.25% | 3.85
Glide | 2 | 3 | 3 | Max |  | PRG | 100% | 2010-04-07: 3 | 0 |  | 50% | -1
Glide | 6 | 2 | 2 | Kojiio |  | ART | 100% | [14 empty] | 0 |  | -66.67% | 4 | bar: 2010-03-30 to 2010-03-31
Glide | 4 | 0.15 | 0.15 | Caio |  | GD | 100% | 2010-03-29: 0.15 | 0 |  | -96.25% | 3.85
Speed Boost | 1 | 0 | 0 | Max |  | PRG | 0% | [14 empty] | 0 |  | -100% | 1
Speed Boost | 4 | 0 | 0 | Kojiio |  | ART | 0% | [14 empty] | 0 |  | -100% | 4
Speed Boost | 4 | 0.15 | 0.15 | Caio |  | GD | 100% | 2010-03-29: 0.15 | 0 |  | -96.25% | 3.85
Autorun | 1 | 0 | 0 | Max |  | PRG | 0% | [14 empty] | 0 |  | -100% | 1
Autorun | 3 | 14 | 14 | kojiio |  | ART | 100% | 2010-03-29: 3; 2010-03-30: 1; 2010-03-31: 2; 2010-04-01: 3; 2010-04-02: 3; 2010-04-05: 2 | 0 |  | 366.7% | -11
Autorun | 4 | 0.15 | 0.15 | Caio |  | GD | 100% | 2010-03-29: 0.15 | 0 |  | -96.25% | 3.85
Camera Holder | 3 | 0 | 0 | Max |  | PRG | 0% | [14 empty] | 0 |  | -100% | 3
Camera Holder | 4 | 0.15 | 0.15 | Caio |  | GD | 100% | 2010-03-29: 0.15 | 0 |  | -96.25% | 3.85
Ingame theme | 0 | 9 | 9 | Caio Audio |  | AUD | 100% | 2010-03-29: 4; 2010-03-30: 4; 2010-03-31: 1 | 0 |  | 0% | -9
SFX | 0 | 3 | 3 | Caio Audio |  | AUD | 100% | 2010-03-31: 3 | 0 |  | 0% | -3
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
FEATURE 03
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
FEATURE 04
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
FEATURE 05
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
FEATURE 06
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
Impediments
[8 empty] | Description |  |  |  | IBL |  |  |  | Found Date |  | Closed Date |  | Solution

## 5. Burndown Task Tables
Silent Runner
Uso Interno
Burndown Task Tables
Task Type Burndown
10 |  | Planned | 2010-03-29 | 2010-03-30 | 2010-03-31 | 2010-04-01 | 2010-04-02 | 2010-04-03 | 2010-04-04 | 2010-04-05 | 2010-04-06 | 2010-04-07 | 2010-04-08 | 2010-04-09 | 2010-04-10 | 2010-04-11
|  |  | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31
Day |  | 10 | 10 | 9 | 8 | 7 | 6 | 5 | 5 | 5 | 4 | 3 | 2 | 1 | 0 | 0
Actual (h) | TOT | 100 | 108 | 98.5 | 99.5 | 89.2 | 89.2 | 89.2 | 89.2 | 89.2 | 89.2 | 89.2 | 69.85 | 69.85 | 69.85 | 69.85
Actual (h) | GD | 36 | 36 | 36 | 36 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 1.35 | 1.35 | 1.35 | 1.35
Actual (h) | ART | 36 | 38 | 26.5 | 27.5 | 38.2 | 38.2 | 38.2 | 38.2 | 38.2 | 38.2 | 38.2 | 35.5 | 35.5 | 35.5 | 35.5
Actual (h) | PRG | 28 | 28 | 28 | 28 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21
Actual (h) | AUD | 0 | 6 | 8 | 8 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 12 | 12 | 12 | 12
Actual (h) | TST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | TOT | 0 | 9.85 | 11.5 | 17 | 6 | 6 | 0 | 0 | 4 | 2.5 | 5 | 8 | 0 | 0 | 0
Productive (h) | GD | 0 | 1.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | ART | 0 | 4.5 | 6 | 7 | 4 | 4 | 0 | 0 | 4 | 0 | 2 | 4 | 0 | 0 | 0
Productive (h) | PRG | 0 | 0 | 1.5 | 6 | 2 | 2 | 0 | 0 | 0 | 2.5 | 3 | 4 | 0 | 0 | 0
Productive (h) | AUD | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | TST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | TOT | 0 | 9.85 | 21.35 | 38.35 | 44.35 | 50.35 | 50.35 | 50.35 | 54.35 | 56.85 | 61.85 | 69.85 | 69.85 | 69.85 | 69.85
Cumulative (h) | GD | 0 | 1.35 | 1.35 | 1.35 | 1.35 | 1.35 | 1.35 | 1.35 | 1.35 | 1.35 | 1.35 | 1.35 | 1.35 | 1.35 | 1.35
Cumulative (h) | ART | 0 | 4.5 | 10.5 | 17.5 | 21.5 | 25.5 | 25.5 | 25.5 | 29.5 | 29.5 | 31.5 | 35.5 | 35.5 | 35.5 | 35.5
Cumulative (h) | PRG | 0 | 0 | 1.5 | 7.5 | 9.5 | 11.5 | 11.5 | 11.5 | 11.5 | 14 | 17 | 21 | 21 | 21 | 21
Cumulative (h) | AUD | 0 | 4 | 8 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
Cumulative (h) | TST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | TOT | 0 | 8 | -9.5 | 1 | -10.3 | 0 | 0 | 0 | 0 | 0 | 0 | -19.35 | 0 | 0 | 0
New Tasks (h) | GD | 0 | 0 | 0 | 0 | -18 | 0 | 0 | 0 | 0 | 0 | 0 | -16.65 | 0 | 0 | 0
New Tasks (h) | ART | 0 | 2 | -11.5 | 1 | 10.7 | 0 | 0 | 0 | 0 | 0 | 0 | -2.7 | 0 | 0 | 0
New Tasks (h) | PRG | 0 | 0 | 0 | 0 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
New Tasks (h) | AUD | 0 | 6 | 2 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0
New Tasks (h) | TST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | TOT | 100 | 98.15 | 77.15 | 61.15 | 44.85 | 38.85 | 38.85 | 38.85 | 34.85 | 32.35 | 27.35 | 0 | 0 | 0 | 0
Remaining (h) | GD | 36 | 34.65 | 34.65 | 34.65 | 16.65 | 16.65 | 16.65 | 16.65 | 16.65 | 16.65 | 16.65 | 0 | 0 | 0 | 0
Remaining (h) | ART | 36 | 33.5 | 16 | 10 | 16.7 | 12.7 | 12.7 | 12.7 | 8.7 | 8.7 | 6.7 | 0 | 0 | 0 | 0
Remaining (h) | PRG | 28 | 28 | 26.5 | 20.5 | 10.5 | 8.5 | 8.5 | 8.5 | 8.5 | 6 | 3 | 0 | 0 | 0 | 0
Remaining (h) | AUD | 0 | 2 | 0 | -4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Remaining (h) | TST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Projection based on total hours avaiable using 75% productivity target
Target Daily (h) | TOT | 10.2 | 10.2 | 10.2 | 10.2 | 10.2 | 10.2 | 0 | 0 | 10.2 | 10.2 | 10.2 | 10.2 | 10.2 | 0 | 0
Target Daily (h) | GD | 2.55 | 2.55 | 2.55 | 2.55 | 2.55 | 2.55 | 0 | 0 | 2.55 | 2.55 | 2.55 | 2.55 | 2.55 | 0 | 0
Target Daily (h) | ART | 3.4 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4 | 0 | 0 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4 | 0 | 0
Target Daily (h) | PRG | 3.4 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4 | 0 | 0 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4 | 0 | 0
Target Daily (h) | AUD | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0 | 0 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0 | 0
Target Daily (h) | TST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secured Limit | TOT | 102 | 91.8 | 81.6 | 71.4 | 61.2 | 51 | 51 | 51 | 40.8 | 30.6 | 20.4 | 10.2 | -1.4211e-14 | -1.4211e-14 | -1.4211e-14
Secured Limit | GD | 25.5 | 22.95 | 20.4 | 17.85 | 15.3 | 12.75 | 12.75 | 12.75 | 10.2 | 7.65 | 5.1 | 2.55 | -3.5527e-15 | -3.5527e-15 | -3.5527e-15
Secured Limit | ART | 34 | 30.6 | 27.2 | 23.8 | 20.4 | 17 | 17 | 17 | 13.6 | 10.2 | 6.8 | 3.4 | 6.2172e-15 | 6.2172e-15 | 6.2172e-15
Secured Limit | PRG | 34 | 30.6 | 27.2 | 23.8 | 20.4 | 17 | 17 | 17 | 13.6 | 10.2 | 6.8 | 3.4 | 6.2172e-15 | 6.2172e-15 | 6.2172e-15
Secured Limit | AUD | 8.5 | 7.65 | 6.8 | 5.95 | 5.1 | 4.25 | 4.25 | 4.25 | 3.4 | 2.55 | 1.7 | 0.85 | 1.5543e-15 | 1.5543e-15 | 1.5543e-15
Secured Limit | TST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Projection based on total ideal hours avaiable using 100% productivity target
Target Daily (h) | TOT | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 0 | 0
Target Daily (h) | GD | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0
Target Daily (h) | ART | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0
Target Daily (h) | PRG | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0
Target Daily (h) | AUD | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Target Daily (h) | TST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Limit | TOT | 120 | 108 | 96 | 84 | 72 | 60 | 60 | 60 | 48 | 36 | 24 | 12 | 0 | 0 | 0
Risk Limit | GD | 30 | 27 | 24 | 21 | 18 | 15 | 15 | 15 | 12 | 9 | 6 | 3 | 0 | 0 | 0
Risk Limit | ART | 40 | 36 | 32 | 28 | 24 | 20 | 20 | 20 | 16 | 12 | 8 | 4 | 0 | 0 | 0
Risk Limit | PRG | 40 | 36 | 32 | 28 | 24 | 20 | 20 | 20 | 16 | 12 | 8 | 4 | 0 | 0 | 0
Risk Limit | AUD | 10 | 9 | 8 | 7 | 6 | 5 | 5 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0
Risk Limit | TST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 6. Burndown Task Graphs
Silent Runner
Uso Interno
Burndown Task Graphics

## 7. Burndown Resources Tables
Silent Runner
Uso Interno
Burndown Resource Tables
Task Type Burndown
10 |  | Planned | 2010-03-29 | 2010-03-30 | 2010-03-31 | 2010-04-01 | 2010-04-02 | 2010-04-03 | 2010-04-04 | 2010-04-05 | 2010-04-06 | 2010-04-07 | 2010-04-08 | 2010-04-09 | 2010-04-10 | 2010-04-11
|  |  | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31
Day |  | 10 | 10 | 9 | 8 | 7 | 6 | 5 | 5 | 5 | 4 | 3 | 2 | 1 | 0 | 0
Actual (h) | TOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual (h) | Max | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual (h) | Caio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual (h) | Kojiio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual (h) | Caio Audio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | TOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | Max | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | Caio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | Kojiio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | Caio Audio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | TOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | Max | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | Caio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | Kojiio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | Caio Audio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | TOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | Max | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | Caio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | Kojiio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | Caio Audio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | TOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | Max | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | Caio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | Kojiio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | Caio Audio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Projection based on total hours avaiable using 75% productivity target
Target Daily (h) | TOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | Max | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | Caio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | Kojiio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | Caio Audio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secured Limit | TOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secured Limit | Max | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secured Limit | Caio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secured Limit | Kojiio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secured Limit | Caio Audio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secured Limit | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secured Limit | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secured Limit | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secured Limit | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secured Limit | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secured Limit | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Projection based on total ideal hours avaiable using 100% productivity target
Target Daily (h) | TOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | Max | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | Caio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | Kojiio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | Caio Audio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Limit | TOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Limit | Max | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Limit | Caio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Limit | Kojiio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Limit | Caio Audio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Limit | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Limit | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Limit | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Limit | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Limit | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Limit | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## CONFIG
HR Type
GD
ART
PRG
AUD
TST